## Feuil1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Tasks | 03/07 - 07/07 | 10/07 - 14/07 | 17/07 - 21/07 | 24/07 - 28/07 | 31/07 - 04/08 | 07/08 - 11/08 | 14/08 - 18/08 | 21/08 - 25/08
Movement tasks | bar: Week 1 to Week 4; Week 6 to Week 8
Getting familiar with the project and with the lab | bar: Week 1
Prepare the setup | bar: Week 1 to Week 2
Movement programing | bar: Week 2 to Week 3
Closed-loop system | bar: Week 1 to Week 4; Week 6 to Week 8
Bibliography reading | bar: Week 3 to Week 4
Set the feedback loop | bar: Week 4; Week 6 to Week 7
Testing and result analysis | bar: Week 8

## Feuil2
|  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8
Tasks |  | 03/07 - 07/07 |  |  |  |  | 10/07 - 14/07 |  |  |  |  | 17/07 - 21/07 |  |  |  |  | 24/07 - 28/07 |  |  |  |  | 31/07 - 04/08 |  |  |  |  | 07/08 - 11/08 |  |  |  |  | 14/08 - 18/08 |  |  |  |  | 21/08 - 25/08
Movement |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Getting familiar with the project and with the lab | bar: 03/07 - 07/07 M to 03/07 - 07/07 T
Prepare the setup | bar: 03/07 - 07/07 W to 10/07 - 14/07 T
Select a spot | bar: 03/07 - 07/07 W
Gather the tools and the linear stages | bar: 03/07 - 07/07 W
Design the adapting parts | bar: 03/07 - 07/07 W to 03/07 - 07/07 T
3D printing of the adapting parts | bar: 03/07 - 07/07 W to 03/07 - 07/07 F
Assemble the stages | bar: 03/07 - 07/07 T to 03/07 - 07/07 F
Wire the stepper motors | bar: 03/07 - 07/07 F to 10/07 - 14/07 M
Design the end effector | bar: 10/07 - 14/07 M to 10/07 - 14/07 T
Movement programing | bar: 10/07 - 14/07 M to 17/07 - 21/07 T
Get familiar with the arduino library controlling the motors | bar: 10/07 - 14/07 M
Code the linear movement of each motor | bar: 10/07 - 14/07 M to 10/07 - 14/07 T
Control the 3 motors together to reach an arbitrary goal (x, y, z) | bar: 10/07 - 14/07 T to 10/07 - 14/07 T
Drag back function | bar: 10/07 - 14/07 T
First tests | bar: 10/07 - 14/07 F
Transfer the setup to its end location | bar: 10/07 - 14/07 F
Identify critical cases | bar: 17/07 - 21/07 M to 17/07 - 21/07 T
Trouble shooting | bar: 17/07 - 21/07 M to 17/07 - 21/07 T
Closed-loop system |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Bibliography reading | bar: W to T
Properly state the constraints of the problem | bar: W
Identify the most suitable algorithm to detect the balls and distinguish them from the flies (computer vision) | bar: W to F
Identify the most suitable algorithm to set the correct goal to the stepper motors | bar: F to T
Set the feedback loop | bar: W to F; M to F
Collect images from the camera | bar: W to T
Implement the chosen computer vision algorithm | bar: T to F
Implement the goal setting algorithm | bar: M to W
Transfer the goal to the stepper motors | bar: W to T
Tests | bar: F to W
Correcting the algorithms according to the results | bar: F to F
Final testing and results analysis | bar: M to F
Testing the final setup and code | bar: M to T
Final troubleshooting | bar: M to T
Report writing and enjoying last days in the lab | bar: W to F